## Table 1
COUNTY: Clalllam Grant No: SEANWS-2023-CLCoCD-00005 PROJECT TITLE: Clallam County MRC Operations and Projects TASK NUMBER: 1-MRC Operations T1.7 Annual Workplan PERIOD COVERED: October 1, 2024 – September 30, 2025 DATE SUBMITTED: January 13, 2025 This project has been funded wholly or in part by the United States Environmental Protection Agency. The contents of this document do not necessarily reflect the views and policies of the Environmental Protection Agency under Assistance Agreement [CE-01J97401]. The contents of this document do not necessarily reflect the views and policies of the Environmental Protection Agency, nor does mention of trade names or commercial products constitute endorsement or recommendation for use.
Clallam County Marine Resources Committee Annual Work Plan: Oct 2024 – Sep 2025
Project |  | October | November | December | January | February | March | April | May | June | July | August | September
MRC Admin | Members | October: Annual Work Plan review. Website update review and suggestions on edits. Begin to develop and plan projects for the next biennium (Oct 2025 - Sept 2027). Quarterly volunteer hours (Jul, Aug, Sep) due by Oct 8.; December: Begin to develop and plan projects for the next biennium (Oct 2025 - Sept 2027). Annual work plan review.; January: Develop and plan projects. Quarterly volunteer hours (Oct, Nov, Dec) due by Jan 12.; February: Develop and plan projects, with project development retreat.; April: Develop and plan projects. Quarterly Volunteer hours (Jan, Feb, Mar) due by April 11.; May: MRC annual presentation to the BOCC.; July: Quarterly Volunteer hours (Apr, May, Jun) due by July 11.
| Members - Advisory | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals. | Track and respond to planning and development proposals.
| Staff | Start of new grant year. Work on annual work plan (due Jan), website updates, and annual report (due Apr). Quarterly reports (Progress report, Matching funds/volunteer time tracking, report of agendas/minutes) due October 15. NWSC monthly report due. Monthly Clallam MRC meeting. | NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. Work on annual report (due Apr). | Finalize annual work plan (due Jan). NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. Work on annual report (due Apr). | Annual work plan due January 14. Quarterly reports (Progress report, Matching funds/volunteer time tracking, report of agendas/minutes) due January 15. NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. Work on annual report (due Apr). Additional staff training with NWSC. | NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. Work on annual report (due Apr). Additional staff training with NWSC. | Finalize annual report (due Apr). NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. | Annual report due April 15. Quarterly reports (Progress report, Matching funds/volunteer time tracking, report of agendas/minutes) due April 15. Complete any new member or MRC member reappointment paperwork. NWSC monthly report due. Monthly Clallam MRC meeting. | NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. | MRC project presentation to the Northwest Straits Commission. NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. | Quarterly reports (Progress report, Matching funds/volunteer time tracking, report of agendas/minutes) due July 15. NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. | NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly. | Closeout report due September 30. NWSC monthly report due. Monthly Clallam MRC meeting. Update website monthly.
| All - Regional Meetings, Trainings, Conferences | November: Northwest Straits Initiative Conference.; December: MRC lead staff meeting.; January: Strait ERN LIO quarterly meeting.; February: NWSC/MRC staff meeting.; April: Strait ERN LIO quarterly meeting.; July: Strait ERN LIO quarterly meeting.; September: NWSC/MRC staff meeting.
| All - Outreach & Education |  |  | Meet with PC staff to establish intern program. | Assess intern mentorship capacity. Potential start to intern program depending on student interest and availability. | Potential mentorship of intern. | Potential mentorship of intern. Plan for festivals, review educational exhibits. | Potential start to intern program depending on student interest and availability. Potentially produce and order new coasters and/or display posters. | Potential mentorship of intern. | Potential mentorship of intern. | Potential start to intern program depending on student interest and availability. | Potential mentorship of intern. Potentially produce and order new coasters and/or display posters. | Host an educational table at Dungeness River Festival and Forever Streamfest if event dates and logistics permit. Potential start to intern program depending on student interest and availability.
Forage Fish Monitoring |  | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Year 2 QAPP due December 31. Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM. | Summary report due September 30. Sampling/monitoring at Cline Spit, Ediz Hook, Elwha East and Elwha West. Enter data into IFORM.
Bull Kelp Monitoring |  | January: NWSC kelp kayak end-of-season meeting. Engage with volunteers to prepare background checks as needed.; April: Year 2 QAPP due April 4.; May: Check all gear to prepare for monitoring. Engage with volunteers and schedule monitoring dates.; June: Attend Olympic Peninsula practice session. Monitor kelp beds and input data.; July: Monitor kelp beds and input data.; August: Monitor kelp beds and input data.; September: Summary report due September 30.
Pigeon Guillemot: Monitoring of breeding colonies |  | April: Year 2 QAPP due April 4.; May: Train volunteers and assign monitoring sites.; June: Weekly monitoring.; July: Summary and training materials due. Weekly monitoring; August: Weekly monitoring.; September: Summary report due September 30. Weekly monitoring as presence dictates.
West Elwha Beach Stewardship |  | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Twice per month filling of doggie waste bags. Surveys of beach users. | Summary report due September 30. Twice per month filling of doggie waste bags. Surveys of beach users.
Olympia Oyster Restoration |  | April: QAPP due April 4.; July: Survey site.; August: Survey site.; September: Year 2 final report due September 30.
Pinto Abalone |  | Initial survey dives. |  | 2024 Pinto abalone final report and copy of 2024 survey data due December 31. |  |  |  | 2025 QAPP addendum due April 10. | Possible survey dives. | Possible survey dives. | Possible survey dives. | Possible survey dives (most likely dates). | Possible survey dives (most likely dates).
Ediz Hook Restoration Planting |  | December: 2024 project report due December 31.; February: Meal approval form submitted prior to planting activity.; March: Possible planting activity.; April: Possible planting activity.
HAZWOPER / Oiled Wildlife Education Training |  | December: 2024 project final report due December 31.; January: 2025 training plan and recruitment materials due January 10.; March: Possible HAZWOPER / oiled wildlife training. Produce training videos for website.
Biotoxins with CCDH |  | October: Sample biotoxins with CCDH bi-weekly.; April: Sample biotoxins with CCDH bi-weekly.; May: Sample biotoxins with CCDH bi-weekly.; June: Sample biotoxins with CCDH bi-weekly.; July: Sample biotoxins with CCDH bi-weekly.; August: Sample biotoxins with CCDH bi-weekly.; September: Sample biotoxins with CCDH bi-weekly.
Sound Toxins with Feiro |  | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. Attend annual 2-day Sound Toxins meeting in Seattle. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday. | Sample with FMLC every Monday.